## Sheet1
Date | Description
2nd October | Github accounts to be update, Jira account to be created for collaboration, work distribution among team members
Ikram will be creating the data base design and implementation,
Rahul, and Dhruv will be creating Wireframes,
Bimlesh/Ranjith will make user-stories, and storyboard
8th October | Discussion about the progress made in the tasks allocated.
11th October | Discussion of Sprint 2
12th October | Meeting to give the final touches to the final submission, updation of honor code and submission of milestone 1
17th October | Task allocation for the project.
Ranjith will be building APIs and python tests for 4 of the wireframes
Dhruv will be taking care of the minutes of meeting
Rahul will be working on the report
Ikram will be working ondatabase design schema